## Workflow Map
Step Number | Step Name | Action | Input | Output | Decision Logic Type | Decision Logic Detail | Boundary Tag | Boundary Rationale | Estimated Time (minutes) | Systems Touched | Notes
1 | Pull CRM account data | Query CRM (e.g. Salesforce) for the account record using the account ID. Retrieve account metadata including ARR, contract dates, tier, key contacts, and recent activity log. | Account ID | Account metadata (ARR, contract dates, tier, key contacts, recent activity log) | None | None — data retrieval. Query CRM using account ID to retrieve a single structured record. No transformation or interpretation required. | AUTOMATE | Pure data retrieval — no judgement involved. If the API call succeeds, you have the data. If it fails, you have an error to handle. No ambiguity, no interpretation, no risk of the agent making a wrong call. | 5 | Salesforce (CRM) | Error path: If API unavailable, flag gap in report and continue with other sources. If account ID not found, halt and alert operator.
2 | Pull support ticket history | Export all support tickets for the account within the quarterly date range. Retrieve ticket list including status, severity, resolution time, and CSAT scores. | Account ID, date range (quarter start and end dates) | Ticket list with status, severity, resolution time, CSAT scores per ticket | None | None — data retrieval. Filter tickets by account ID and date range. No transformation, no interpretation — the system returns a complete list or an empty result. | AUTOMATE | Pure data retrieval with deterministic query parameters (account ID + date range). No judgement required — the API returns a complete ticket list or an error. | 5 | Zendesk (Support platform) | Error path: If API unavailable, flag gap in report and continue with other sources. If empty result, verify date range is correct and note "no tickets filed this quarter" — do not infer anything from absence of tickets.
3 | Pull product usage metrics | Access the product analytics platform API or data warehouse. Query for account-level usage statistics within the quarterly date range including active users, feature adoption rates, API call volume, and error rates. | Account ID, date range (quarter start and end dates) | Usage stats: active users, DAU/MAU ratio, feature adoption percentage, API call volume, error rates | None | None — data retrieval. Query usage API or data warehouse for account-level metrics within the date range. May require multiple API calls if metrics are spread across endpoints. | AUTOMATE | Pure data retrieval. Usage metrics are numerical and unambiguous — the system returns them or it doesn't. No interpretation required at this stage. | 5 | Mixpanel (Product analytics) | Error path: If API or data warehouse unavailable, flag gap in report and continue. May need custom extraction logic depending on data warehouse setup. Pagination may be required for high-volume accounts.
4 | Pull recent Slack/comms context | Search Slack channels for mentions of the account name and key contact names. Retrieve all matching message threads from the quarter. Cast a wide net — over-retrieve rather than miss relevant context. | Account name, key contact names (from Step 1 output) | Relevant Slack message threads mentioning the account or its contacts | None | None — search and retrieve. Use account name and key contact names as search queries against Slack API search.messages endpoint. No filtering or interpretation at this stage — retrieval only. | AUTOMATE | Pure search and retrieval. The agent uses account name and contact names as search terms. Results will contain noise, but filtering and interpretation happen in the next step (Step 5). No judgement applied here. | 10 | Slack | Error path: If Slack API rate-limited, implement pagination with backoff and retry. If no results found, note "no Slack activity for this account this quarter" rather than omitting. Over-retrieve to ensure coverage — the human filters in Step 5.
5 | Review Slack context for sentiment signals | Read through all retrieved Slack threads. Assess the overall tone of customer communications. Identify explicit complaints, escalation language, positive signals, and unresolved concerns. Produce an annotated sentiment summary with supporting quotes. | Slack message threads from Step 4 | Annotated sentiment summary: overall tone (positive / neutral / negative / mixed), key quotes, unresolved concerns, sentiment trend direction | Contextual judgement | Read threads and assess tone — is the customer happy, frustrated, or neutral? Look for explicit complaints ("this is broken", "unacceptable"), escalation language ("we need to talk", "escalating this"), positive signals ("love the new feature", "great support response"), and unresolved concerns that received no response. Consider thread context: who is speaking (champion vs. detractor vs. end-user), whether concerns received timely responses, recency of sentiment shifts (last 30 days weighted more heavily), and volume of communication (silence can signal disengagement). The agent summarises threads and proposes a sentiment reading; the human validates using relationship context the agent cannot access. | HUMAN-IN-THE-LOOP | Slack conversations contain sarcasm, inside jokes, off-topic tangents, and genuine product complaints mixed together. An LLM can summarise threads and propose a sentiment reading, but the CSD knows the relationship context that determines whether "we need to talk about the roadmap" is a routine quarterly planning request or a veiled threat to churn. The agent does the heavy lifting (summarise, propose); the human validates. | 20 | Slack (output from Step 4) | Error path: If no relevant threads found, mark sentiment as "insufficient data" rather than guessing neutral. If threads are ambiguous or contradictory, present both interpretations and flag for human resolution. The agent should surface direct quotes to support its proposed sentiment reading.
6 | Assess ticket health | Analyse ticket volume trends, severity distribution, resolution times vs SLA targets, and CSAT scores. Compare this quarter against the prior quarter. Produce a ticket health assessment with a clear improving/stable/degrading rating and supporting evidence. | Ticket data from Step 2, SLA benchmark targets (from config) | Ticket health assessment: rating (improving / stable / degrading), SLA compliance percentage, CSAT trend, key issues list, risk escalation flags | Criteria-based | Evaluate first response time and resolution time against SLA targets by severity — P1: 30min response / 4hr resolution, P2: 2hr / 24hr, P3: 8hr / 72hr, P4: 24hr / 168hr. Flag if SLA compliance drops below 95% of tickets resolved within target. Flag if CSAT falls below 4.0/5. Compare ticket volume and average severity against prior quarter: a >20% volume increase or upward severity shift (e.g. average moving from Low to Medium/High) indicates degradation. If both volume and severity worsen simultaneously, escalate to the risk register. Classify overall ticket health as: Improving (volume down or SLA compliance up QoQ), Stable (all metrics within 10% of prior quarter), or Degrading (any flag triggered). | AUTOMATE (quantitative) / HUMAN-IN-THE-LOOP (edge cases) | Quantitative calculations (trend analysis, SLA compliance rates, CSAT averages) are deterministic and fully automatable — two agents given the same data would produce identical results. But interpretation of edge cases requires context the agent does not have. Example: a spike in ticket volume might look alarming, but the CSD knows it was caused by a planned migration and is therefore benign. The split boundary lets the agent handle the math while the human handles the meaning. | 15 | Zendesk (output from Step 2), SLA benchmarks config file | Error path: If SLA benchmarks config is missing, use industry-standard defaults and flag for review. If ticket data is incomplete (missing severity or resolution time fields), calculate metrics on available data and note gaps. Decision logic entries here become config/scoring_rubric.yaml in Stage 5.
7 | Assess product engagement | Analyse usage trends across three core metrics: DAU/MAU ratio, feature adoption percentage, and API call volume. Compare each metric against tier-specific benchmarks and against the prior quarter. Produce an engagement assessment with a clear healthy/at-risk/critical rating. | Usage data from Step 3, tier-specific benchmark thresholds (from config) | Engagement assessment: rating (healthy / at-risk / critical), per-metric scores vs benchmarks, trend direction (improving / stable / declining), flagged degradation signals | Criteria-based | Evaluate three metrics against tier-specific benchmarks — DAU/MAU ratio (enterprise: ≥40%, mid-market: ≥30%, SMB: ≥25%), feature adoption percentage (enterprise: ≥60%, mid-market: ≥45%, SMB: ≥35%), and API call volume floor (enterprise: 10K/month, mid-market: 2K, SMB: 500). A quarter-over-quarter decline of >15% in any single metric flags a degrading trend. Classify overall engagement as: Healthy (all metrics at or above tier benchmark with stable or improving trend), At-risk (any metric 10–25% below tier benchmark or declining for 2+ consecutive months), Critical (any metric >25% below benchmark or >15% QoQ decline). If account tier is missing from config, flag and request manual classification before proceeding. | AUTOMATE (quantitative) / HUMAN-IN-THE-LOOP (context) | Tier-specific benchmark comparisons and trend calculations are deterministic — the math produces the same result every time. But usage context matters: a drop in DAU/MAU during a customer's holiday season or a known company-wide event is expected, not alarming. A sudden spike in API errors might indicate a product issue, not a customer engagement problem. The human provides the contextual interpretation that numbers alone cannot convey. | 15 | Mixpanel (output from Step 3), tier benchmarks config file | Error path: If benchmark config is missing for the account's tier, flag and request manual input before scoring. If usage data is partial (e.g. DAU/MAU available but feature adoption missing), score available metrics and note gaps. These tier-specific criteria become externalised config in Stage 5.
8 | Identify risks and opportunities | Synthesise findings from Steps 5-7 with the contract timeline from Step 1. Cross-reference sentiment, ticket health, and engagement signals to identify compound risk patterns and expansion opportunities. Produce a prioritised risk register and opportunity list. | All prior step outputs (sentiment summary, ticket health assessment, engagement assessment), contract renewal date and ARR from Step 1 | Prioritised risk register (risk description, severity, evidence, recommended action) + opportunity list (opportunity description, evidence, recommended next step) | Contextual judgement | Synthesise findings across all dimensions and match against known risk/opportunity patterns. Key patterns: declining usage + upcoming renewal within 90 days = high churn risk; high feature adoption + usage above tier ceiling = upsell opportunity; negative sentiment + open P1/P2 tickets = escalation risk requiring immediate attention; positive sentiment + feature requests in Slack = expansion signal. Weigh recency of signals — a sentiment shift in the last 30 days matters more than one from 60+ days ago. Cross-reference risk signals against account tier and ARR to prioritise by business impact (high-ARR accounts with red signals get top priority). The agent proposes a risk register and opportunity list; the human validates against relationship context and knowledge of ongoing conversations not captured in data. | HUMAN-IN-THE-LOOP | Risk and opportunity identification requires synthesising multiple qualitative and quantitative signals and applying relationship context that exists only in the CSD's head. The agent can flag patterns (declining usage + upcoming renewal) and propose a risk register, but the CSD knows whether a flagged risk is already being actively managed, whether an opportunity is politically viable given the customer's budget cycle, or whether a "negative" signal is actually a positive sign of deepening engagement. | 20 | All prior step outputs, Salesforce (contract renewal dates, ARR) | Error path: If one or more input assessments are missing (e.g. Slack sentiment unavailable due to API failure), generate a partial risk register and flag gaps explicitly — do not silently omit dimensions. If contract data is missing, flag that renewal timeline cannot be factored into risk assessment.
9 | Assign overall health score | Rate the account on the health framework using the Green/Amber/Red scoring rubric. Evaluate each of the four dimensions (tickets, usage, sentiment, contract) independently, then assign an overall score based on the most severe dimension. Provide a written justification referencing the specific criteria that drove the rating. | All prior step outputs (ticket health assessment from Step 6; engagement assessment from Step 7; sentiment summary from Step 5; contract data from Step 1; risk register from Step 8) | Overall health score (Green / Amber / Red) with per-dimension sub-scores and a written justification paragraph | Criteria-based | Apply Green/Amber/Red rating across four dimensions — tickets, usage, sentiment, and contract. Green: SLA compliance ≥95%, no open P1s, CSAT ≥4.0; DAU/MAU and feature adoption at or above tier benchmark with stable or improving trend; neutral-to-positive sentiment with no unresolved escalations; no renewal within 90 days, or renewal approaching with no risk signals. Amber: SLA compliance 80–95%, or unresolved P2+ tickets open >7 days, or CSAT 3.5–4.0; metrics 10–25% below tier benchmark or declining for 2+ consecutive months; mixed sentiment with some concerns; renewal within 90 days with one or more amber signals in other dimensions. Red: SLA compliance <80%, or any open P1, or CSAT <3.5; any metric >25% below benchmark or >15% QoQ decline; negative tone or active escalation or executive complaint; renewal within 60 days with any red signal in another dimension. Assign the overall score as the most severe rating triggered by any single dimension. When dimensions conflict (e.g. green tickets but red sentiment), weight sentiment and contract risk more heavily — dissatisfied customers with upcoming renewals are the highest priority regardless of other metrics. | HUMAN-IN-THE-LOOP | The scoring rubric itself is criteria-based and the quantitative scoring is automatable, but the final health score assignment is HIL because these scores drive account strategy decisions with significant business consequences — resource allocation, executive attention, renewal negotiation approach. The human validates that the rubric-derived score matches their holistic understanding of the account, catching cases where the rubric produces a technically correct but contextually misleading result (e.g. a Green score for an account the CSD knows is quietly evaluating competitors). | 10 | All prior step outputs, health framework criteria config | Error path: If any dimension cannot be scored due to missing data, assign that dimension as "Unable to score — insufficient data" and note the gap in the justification. Do not default missing dimensions to Green. These criteria become the core of config/scoring_rubric.yaml in Stage 5.
10 | Generate health report | Write a structured report using the standard template with sections for each dimension: ticket health, product engagement, sentiment analysis, risk register, opportunity list, and overall health score. Each section includes metric summary, trend analysis, key findings, and recommended actions. Populate all sections from prior step outputs. | All prior step outputs (Steps 1-9), report template | Formatted health report document (Markdown or HTML) with all sections populated, per-dimension detail, and recommended actions | None | None — template-based generation. Populate the standard report template with data and assessments from prior steps. Each section follows a fixed structure: metric summary, trend vs prior quarter, key findings, recommended actions. No new analysis or judgement — this step assembles and formats existing outputs into a coherent narrative document. | AUTOMATE (draft) / HUMAN-IN-THE-LOOP (review) | Report structure is template-based and all content has been validated in prior HIL steps. The agent generates a complete draft; the human reviews for narrative coherence, tone appropriateness, and any sensitive content that needs rewording or emphasis adjustment before it goes to the exec summary step. | 15 | All prior step outputs, report template | Error path: If report template is missing or malformed, generate a plain-text structured report with standard section headers and flag for manual formatting. If any prior step output is missing, include the section with a placeholder noting "data unavailable" rather than omitting the section entirely. Output as Markdown or HTML.
11 | Generate exec summary | Write a 3-5 sentence executive summary distilling the full health report into the key message. Lead with overall health status, follow with the single most important risk or opportunity, close with the recommended next action. Calibrate tone to the executive audience. | Health report from Step 10, overall health score from Step 9 | Executive summary paragraph (3-5 sentences): overall status, top risk or opportunity, recommended action | Contextual judgement | Distill the full health report into a 3-5 sentence executive summary. Lead with overall health status (Green/Amber/Red and what it means in plain language). Follow with the single most important risk or opportunity — the one thing the reader must know. Close with the recommended next action or ask. Calibrate tone to the audience: executives want the "so what" and the ask, not the methodology or the data. If the account is Red, lead with the risk and the urgency of the ask. If Green, lead with the opportunity and momentum. If Amber, lead with what is changing and what decision is needed. Avoid hedging language ("might", "could potentially") — be direct about what the data shows and what you recommend. | AUTOMATE (draft) / HUMAN-IN-THE-LOOP (tone) | The agent can draft a competent summary from structured report data, but executive communication requires tone calibration and political sensitivity that the agent cannot evaluate. The human adjusts emphasis (what to highlight vs. downplay), manages framing for the specific executive audience, and ensures the summary will land correctly with the reader. A tone-deaf exec summary undermines trust in the entire report. | 10 | Health report from Step 10 | Error path: If health report from Step 10 is incomplete, generate summary from available sections and explicitly flag gaps ("Note: sentiment data unavailable for this quarter"). The tone review is critical — an AI-generated summary that reads as generic or tone-deaf to the executive audience undermines trust in the entire workflow.
12 | Final review and distribution | Review the complete report package (health report + exec summary) for accuracy, completeness, tone, and political sensitivity. Verify that narrative sections are consistent with scored dimensions. Check that sensitive account details are appropriately framed. Select the distribution list (varies by account based on stakeholder preferences and org structure). Make final edits to wording, emphasis, and framing. Send to stakeholders via email or internal communication platform. | Complete report package (health report from Step 10, exec summary from Step 11), stakeholder contact list | Distributed report package sent to appropriate stakeholders | Contextual judgement | Review the complete package for: (1) Accuracy — do narrative sections match the scored dimensions? (2) Completeness — are all sections present and populated? (3) Tone — is the language appropriate for the audience and the account situation? (4) Political sensitivity — is there anything that needs rewording or omitting given current account dynamics? (5) Distribution list — who should receive this report? The list may vary by account based on stakeholder preferences, org changes, or current account dynamics (e.g. adding a new VP who just joined, removing someone who left). Make final edits and send. | MANUAL | Distribution is irreversible — once the report is sent, it is sent. The CSD needs to make final judgement calls about tone, completeness, and political sensitivity. The distribution list requires relationship knowledge the agent cannot access (who is in, who is out, who needs a heads-up before the formal report). This is a deliberate safety boundary — keeping this step fully manual is not a limitation, it is a design choice. | 15 | Email / communication platform, complete report package | Error path: N/A — this is a fully manual step. The human is the error handler. Do not attempt to automate distribution in v1. This is the strongest safety boundary in the workflow. The boundary can be reconsidered in future versions as trust builds.

## Data Inventory
Data Source | System/Platform | Access Method | Data Format | Authentication Required | Rate Limits or Pagination | Data Quality Notes | Which Workflow Steps Use This Source | API Documentation URL | Notes
CRM — account metadata | Salesforce | REST API (Salesforce REST API — query account object by account ID, retrieve fields: ARR, contract dates, tier, key contacts, recent activity log) | JSON | OAuth token (connected app with refresh token flow) | Salesforce API: 100K requests/day for Enterprise edition. Single account query is one API call — well within limits. Pagination not needed for single-account retrieval. | Account data is generally reliable and up-to-date as CSDs maintain it. Potential gaps: key contacts list may be stale if the CSD hasn't updated it after an org change. Contract dates are authoritative. Recent activity log may not capture all touchpoints if CSDs log inconsistently. | Steps 1, 8, 9 | (org-specific Salesforce API docs) | Need account-level read permissions at minimum. The connected app must have the correct OAuth scopes for account object access. Contract renewal date from this source is critical for risk assessment in Step 8.
Support platform — ticket history | Zendesk | REST API (Zendesk Search API — query tickets by account/organisation ID and created_at date range, retrieve: status, severity/priority, resolution time, first response time, CSAT rating) | JSON | API key (Zendesk API token or OAuth token) | Zendesk API: rate limit of 400 requests per minute. For accounts with high ticket volumes (>500 tickets/quarter), results will be paginated — implement cursor-based pagination. Each page returns up to 100 results. | Ticket data is structured and reliable. Known gaps: CSAT scores are only present on tickets where the customer completed the survey (typically 30-40% response rate) — do not treat absence of CSAT as negative. Resolution time may be skewed by tickets reopened after initial closure. Severity classifications (P1-P4) depend on consistent triage by the support team. | Steps 2, 6 | (org-specific Zendesk API docs) | Filter by account/organisation ID + date range for the quarter. Need to handle the CSAT response rate gap explicitly — report CSAT on responded tickets only, with response rate noted. P1-P4 severity levels must match the SLA benchmark config.
Product usage data | Mixpanel | REST API (Mixpanel Engage API or JQL for user-level queries, or Export API for raw event data) or data warehouse query (if usage data is replicated to a warehouse like BigQuery or Snowflake) | JSON (API) or CSV (warehouse export) | API key (Mixpanel project API secret) or database credentials (for warehouse) | Mixpanel Export API: rate limit varies by plan — typically 60 requests per hour for raw export. JQL queries: 2 concurrent queries, 5 per minute. Data warehouse queries: depends on warehouse plan and query complexity. For high-volume accounts, prefer warehouse over API. | Usage data accuracy depends on event instrumentation. Known issues: feature adoption metrics may undercount if features were instrumented after launch (historical gap). DAU/MAU ratio can be noisy for accounts with seasonal usage patterns. API call volume is authoritative from server-side logging. Error rates may include both client-side and server-side errors — clarify which is captured. | Steps 3, 7 | (org-specific Mixpanel or warehouse docs) | May need custom extraction logic depending on how usage data is stored. If using data warehouse, ensure the replication pipeline is current (check last sync timestamp). Feature adoption percentage requires a defined list of "core features" per tier — this should be in config alongside tier benchmarks.
Slack — customer communications | Slack | Slack API (search.messages endpoint — search by account name and key contact names across relevant channels) | JSON | Bot token (Slack bot token with search:read scope and channels:history scope for relevant channels) | Slack API: search.messages is rate-limited to 20 requests per minute (Tier 2). Results are paginated with up to 100 messages per page. For active accounts, expect 3-10 pages of results requiring sequential pagination calls with backoff. | Slack data is inherently noisy. Search results will include false positives (account name appearing in unrelated contexts), off-topic messages in customer channels, internal side conversations, and automated bot messages. Signal-to-noise ratio varies significantly by account — active accounts with dedicated channels produce cleaner results than accounts discussed in shared channels. Messages may be edited or deleted after retrieval. | Steps 4, 5 | (org-specific Slack API docs — search.messages endpoint) | The bot must be a member of all relevant channels to search them. If the bot lacks access to private channels where account discussions happen, results will be incomplete. Over-retrieve by design — filtering and interpretation happen in Step 5 (HIL). Consider caching search results to avoid re-querying during the same workflow run.
SLA benchmark targets | Internal config file | File system read (load from config/scoring_rubric.yaml or equivalent structured config file, or retrieve from internal documentation system) | Structured text / JSON / YAML | File system access (no external auth — local or repo-hosted config file) | N/A — static file, no rate limits. File is read once at workflow start and cached for the duration of the run. | SLA benchmarks should be treated as authoritative if they are maintained by the support operations team. Risk: if the config file is outdated (e.g. SLA targets changed last quarter but config wasn't updated), the ticket health assessment in Step 6 will use stale thresholds. Verify last-modified date on config file and flag if >90 days old. | Steps 6, 9 | N/A — internal file | Contains SLA response and resolution targets by severity level (P1-P4) and CSAT threshold. This is a candidate for externalisation as config in Stage 5 — define once, load at runtime, update without code changes. If this file doesn't exist yet, it must be created during Stage 5 build using the criteria captured in the Step 6 and Step 9 Decision Logic Detail columns.
Health scoring framework / tier benchmarks | Internal config file | File system read (load from config/scoring_rubric.yaml — the same file as SLA benchmarks, or a separate config/tier_benchmarks.yaml) | Structured text / JSON / YAML | File system access (no external auth — local or repo-hosted config file) | N/A — static file, no rate limits. File is read once at workflow start and cached. | Scoring framework must be complete and internally consistent. Known risk: if different teams use slightly different definitions of Green/Amber/Red, the config must reflect the CSD team's agreed-upon version. Tier-specific benchmarks (DAU/MAU, feature adoption, API volume thresholds) must cover all tiers the account base includes — if a new tier is introduced, the config must be updated before the workflow runs. | Steps 7, 9 | N/A — internal file | Contains Green/Amber/Red criteria across four dimensions (tickets, usage, sentiment, contract) and tier-specific engagement benchmarks (enterprise, mid-market, SMB). This is the second candidate for Stage 5 config externalisation. If the scoring framework changes frequently (e.g. quarterly revisions), it must be versioned and the workflow should log which version was used for each report.

## Integration Requirements
Requirement Category | Specific Requirement | Version or Specification | Status | Owner | Notes
Framework | LangGraph — agent orchestration framework for defining the workflow as a state machine with nodes and edges | LangGraph ≥0.2 (Python) — requires langgraph package | Needs Setup | Developer / Builder | Core dependency. The workflow map steps translate into LangGraph nodes in Stage 4. Each AUTOMATE step becomes a tool-calling node, each HIL step becomes an interrupt-before checkpoint. Install via pip install langgraph.
Framework | LangChain — tool wrappers and abstractions for data source integrations | LangChain ≥0.3 (Python) — requires langchain and langchain-community packages | Needs Setup | Developer / Builder | Used for tool abstractions that wrap each data source API. Provides standardised interfaces for the agent to call Salesforce, Zendesk, Mixpanel, and Slack APIs as tools. Install via pip install langchain langchain-community.
LLM Provider | Anthropic SDK — Claude API access for synthesis / summarisation / report generation | Anthropic Python SDK ≥0.39 (anthropic package), Claude model (claude-sonnet-4-20250514 or later recommended) | Needs Setup | Developer / Builder | Required for Steps 5, 8, 9, 10, and 11 where the agent synthesises data, applies contextual judgement, or generates narrative text. API key must be provisioned and stored securely. Consider claude-sonnet-4-20250514 for cost-efficiency on data retrieval nodes, Claude Opus for synthesis and report generation nodes.
Data Source API | Salesforce REST API — account object read access | Salesforce REST API v59.0+, requires connected app with OAuth 2.0 flow | Needs Setup | Salesforce Admin / IT | Required for Step 1. Need a connected app configured with OAuth refresh token flow. Required OAuth scopes: api, read for account object. The connected app must be authorised for the Salesforce org containing account data.
Data Source API | Zendesk REST API — ticket search and retrieval | Zendesk API v2, search endpoint for tickets by organisation and date range | Needs Setup | Zendesk Admin / IT | Required for Step 2. Need an API token or OAuth token with read access to tickets. Must be able to filter by organisation (account) and created_at date range. Handle pagination for accounts with >100 tickets per quarter.
Data Source API | Mixpanel API or data warehouse — product usage metrics retrieval | Mixpanel Engage API / JQL / Export API, or BigQuery/Snowflake SQL access if usage data is replicated | Needs Investigation | Data / Analytics Team | Required for Step 3. Access method depends on how usage data is stored — direct Mixpanel API, or query against a data warehouse replica. Needs investigation to determine which path is available and which provides the required metrics (DAU/MAU, feature adoption, API call volume, error rates).
Data Source API | Slack API — message search across customer channels | Slack Web API (search.messages endpoint), requires bot token with search:read and channels:history scopes | Needs Setup | Slack Admin / IT | Required for Step 4. The bot must have search scope and must be a member of all relevant customer channels. If customer discussions happen in private channels, the bot needs explicit invitation to each. Rate limit: 20 requests/minute — implement backoff.
Authentication | Credentials management — secure storage and retrieval of all API keys and tokens | Environment variables for local development, secrets manager (e.g. AWS Secrets Manager, HashiCorp Vault, or .env with python-dotenv) for deployment | Needs Setup | Developer / Builder + IT | All data source credentials (Salesforce OAuth tokens, Zendesk API key, Mixpanel API secret, Slack bot token, Anthropic API key) must be stored securely and never hardcoded. For local development, .env file with python-dotenv is acceptable. For production, use a secrets manager. Document the required environment variables in the project README.
Authentication | Salesforce OAuth refresh token — long-lived token for unattended API access | OAuth 2.0 refresh token flow, token refresh handled automatically by the Salesforce client library | Needs Setup | Salesforce Admin | Salesforce OAuth tokens expire — the integration must handle token refresh automatically. The connected app must be configured to issue refresh tokens. Store the refresh token securely; it grants ongoing access to account data.
Output Format | Markdown or HTML report generation — formatting the health report and exec summary | Python markdown library or Jinja2 templates for HTML generation | Needs Setup | Developer / Builder | Required for Steps 10 and 11. The report template should be defined as a Jinja2 template (or equivalent) that the agent populates with structured data from prior steps. Output as Markdown for internal review, HTML for distribution. Consider adding PDF export as a future enhancement.
Output Format | Report template file — standard structure for the health report | Jinja2 template (.j2) or Markdown template (.md) stored in the project's templates/ directory | Needs Setup | Developer / Builder + CSD Team | The report template must be defined collaboratively with the CSD team to ensure it matches their current report structure and expectations. Template sections: Executive Summary, Ticket Health, Product Engagement, Sentiment Analysis, Risk Register, Opportunities, Overall Health Score, Recommended Actions.
Infrastructure | Python runtime environment | Python ≥3.11 with virtual environment (venv or conda) | Available | Developer / Builder | All framework dependencies (LangGraph, LangChain, Anthropic SDK) require Python 3.11+. Use a virtual environment to isolate dependencies. A requirements.txt or pyproject.toml should pin all dependency versions.
Infrastructure | LangGraph checkpointing — persistence for HIL interrupt/resume workflow | LangGraph MemorySaver (development) or SqliteSaver / PostgresSaver (production) | Needs Setup | Developer / Builder | LangGraph's interrupt-before mechanism (used for HIL steps) requires a checkpointer to persist state between human review cycles. MemorySaver is fine for development; production needs durable storage. This is a Stage 5 build decision but should be planned for now.

## Constraints & Assumptions
Assumption Category | Assumption Statement | What Would Break If Wrong | Verified? | Impact If Wrong | Mitigation or Fallback | Notes
Entity cardinality | Each account has exactly one active product. The health scoring workflow evaluates a single product's usage metrics, ticket history, and engagement data per account. | If an account has multiple active products, the health scoring step (Step 9) would produce a single score that conflates the health of different products — a healthy Product A could mask a failing Product B. The engagement assessment (Step 7) would need to evaluate and weight each product separately, the state schema in Stage 4 would need a product-level loop, and the scoring rubric in Stage 5 would need per-product dimensions. | Needs investigation | Stage 3 (workflow map Steps 7 and 9 would need product-level sub-steps), Stage 4 (state schema needs a product-level loop within the account-level workflow), Stage 5 (scoring rubric config needs per-product dimensions and a product-weighting strategy) | If multi-product accounts exist: (1) add a product enumeration step after Step 1 that lists active products per account, (2) loop Steps 3, 7, and 9 per product, (3) add a product-level health roll-up step that aggregates into an account-level score. Alternatively, scope v1 to single-product accounts only and flag multi-product accounts for manual review. | THIS IS THE ASSUMPTION MOST LIKELY TO BE MISSED. It is invisible because the worked example implicitly assumes one product per account. Surface this explicitly during scoping and verify against the actual account base before proceeding to Stage 4.
Entity cardinality | Each account has one primary CSD (Customer Success Director) who owns the review and has the relationship context needed for HIL steps. The workflow does not account for shared ownership, account transitions, or accounts in a handover state. | If an account has shared ownership or is mid-transition between CSDs, the HIL steps (5, 6, 7, 8, 9, 11, 12) may route to a reviewer who lacks the full relationship context. Sentiment interpretation (Step 5) and risk identification (Step 8) depend on deep account knowledge that a new or secondary owner may not have. | Needs investigation | Stage 4 (HIL routing logic may need to support multiple reviewers or a primary/secondary reviewer model), Stage 12 (distribution list approval may require sign-off from both outgoing and incoming CSD during transitions) | For v1, require that the CSD running the workflow is the current primary owner with full account context. Flag accounts in transition for manual processing. Add a pre-flight check at workflow start that confirms the operator is the current account owner. | Accounts in transition are a known pain point in CS orgs. The workflow should surface this constraint rather than silently assuming single ownership.
Temporal / frequency | The workflow runs on a quarterly cadence (once per quarter per account) and all data sources provide data that is current as of the quarter-end date. Metrics are compared quarter-over-quarter using aligned quarterly boundaries. | If the workflow runs mid-quarter or on a different cadence, the quarter-over-quarter comparisons in Steps 6 and 7 would compare partial quarters against full quarters, producing misleading trend data. If data sources have different refresh rates (e.g. Mixpanel data lags by 48 hours but Zendesk is real-time), metrics from the same nominal date range may represent different actual time windows. | No | Stage 3 (date range parameters in Steps 2-4 need to account for data freshness lag), Stage 5 (data retrieval nodes need configurable date ranges with freshness checks) | Define explicit date range parameters at workflow start (quarter_start, quarter_end) rather than calculating from current date. Add a data freshness check: for each data source, verify that the most recent data point falls within the expected range. If any source lags by >72 hours, flag the gap in the report header. | If the workflow is later adapted to monthly or ad-hoc cadence, the comparison logic in Steps 6-7 and the scoring thresholds in Step 9 would need recalibration — thresholds calibrated for quarterly trends may over- or under-flag on shorter time horizons.
Temporal / frequency | Support ticket data (Zendesk) is available in near-real-time via API, and ticket metadata (severity, resolution time, CSAT) is populated at the time of query. | If ticket data has a processing delay (e.g. CSAT scores are only populated 24-48 hours after ticket closure), the ticket health assessment in Step 6 could miss recent resolutions or use incomplete CSAT data for recently closed tickets. The SLA compliance calculation could count tickets as still-open that were resolved but not yet synced. | Needs investigation | Stage 5 (data retrieval node for Zendesk may need a staleness buffer — e.g. only evaluate tickets closed ≥48 hours ago for CSAT completeness) | Run the workflow 48-72 hours after quarter-end to allow ticket metadata to fully populate. Alternatively, add a CSAT completeness check: if >10% of closed tickets lack CSAT scores, note the gap and calculate CSAT on responded tickets only with the response rate disclosed. | This is a common data quality issue with support platforms. The CSAT response rate gap is already noted in the Data Inventory, but the timing dependency is a separate constraint.
Access / permissions | All six data sources (Salesforce, Zendesk, Mixpanel, Slack, SLA config, health framework config) have programmatic API access with appropriate read permissions granted to the agent's service account or bot identity. | If any data source requires manual export (e.g. product usage data is only available via a dashboard CSV download, or Slack channels require manual search because the bot lacks channel membership), the corresponding Steps 1-4 cannot be automated. The AUTOMATE boundary tag for those steps would need to change to MANUAL, fundamentally altering the workflow's automation profile. | Needs investigation | Stage 3 (boundary tags for Steps 1-4 may need revision), Stage 4 (manual steps cannot become LangGraph nodes — they become external dependencies with wait states), Stage 5 (build scope shrinks if data retrieval is manual) | For each data source, verify API access before starting Stage 4. If a source lacks API access: (1) check if an API can be enabled (e.g. Slack bot permissions), (2) if not, check if a scheduled export can serve as a workaround (e.g. nightly CSV export from Mixpanel to a shared drive), (3) if neither, reclassify the step as MANUAL and adjust the workflow map. | This is the single most common blocker in practice. Teams assume API access exists and discover during build that permissions haven't been granted, the API doesn't expose the needed fields, or the API requires an upgrade to a higher platform tier.
Access / permissions | The agent will not have direct access to send the final report to stakeholders — distribution (Step 12) remains entirely manual. The agent produces the report; the human sends it. | If the agent were granted send access (e.g. email API or Slack message posting), the irreversibility risk at Step 12 increases dramatically. A malformed, incomplete, or tone-deaf report sent automatically to executives cannot be unsent. The safety boundary that makes the entire workflow trustworthy depends on this constraint. | Yes | Stage 3 (if reversed, Step 12 boundary would change from MANUAL to AUTOMATE or HIL, requiring a new approval checkpoint), Stage 4 (would need a confirmation node with explicit human approval before send), Stage 5 (would need email/Slack integration with send permissions) | Maintain this as a hard constraint for v1. If distribution automation is desired in future versions, implement it as a two-step process: (1) agent prepares the distribution (draft email, recipient list) and presents for approval, (2) human clicks a single confirm button to send. Never auto-send without explicit human confirmation. | This is a deliberate safety boundary, not a limitation. Keeping distribution manual is a design choice that makes the rest of the automation trustworthy. Revisit only after multiple quarters of successful operation.
Access / permissions | Slack bot token has search:read scope and the bot is a member of all relevant customer channels (including private channels where account-specific discussions occur). | If the bot lacks access to private channels, Slack search results (Step 4) will be incomplete — potentially missing the most sensitive and informative discussions about the account. The sentiment analysis in Step 5 would be based on an incomplete picture, potentially producing a falsely neutral or positive sentiment reading. | Needs investigation | Stage 3 (Step 4 output quality degrades, Step 5 sentiment accuracy drops), Stage 5 (Slack integration setup must include channel membership verification) | Before workflow launch, audit which channels discuss each account and verify bot membership. For channels where the bot cannot be added (e.g. confidential executive channels), document the gap and instruct the CSD to manually supplement the Slack data during the Step 5 HIL review. Add a completeness note to Step 5 output: 'Slack coverage: X of Y known channels searched.' | Slack channel access is often fragmented — some discussions happen in public channels, some in private, some in DMs. The bot will never have complete coverage. The Step 5 HIL checkpoint exists partly for this reason.
Stability / change rate | The health scoring framework (Green/Amber/Red criteria, SLA targets by severity, tier-specific engagement benchmarks) is defined, agreed upon by the CSD team, and stable for at least the current quarter. No mid-quarter changes to scoring thresholds or tier definitions. | If scoring criteria change mid-quarter, accounts reviewed before the change would have different scores than accounts reviewed after — producing inconsistent health ratings across the portfolio. Quarter-over-quarter comparisons would be invalid because the baseline changed. Trust in the scoring system erodes if stakeholders notice inconsistencies. | Needs investigation | Stage 5 (config/scoring_rubric.yaml would need versioning — each report must record which config version was used), Stage 3 (if criteria change frequently, the constraint should be relaxed and the workflow should include a config version check at startup) | Externalise all scoring criteria as config (this is already planned for Stage 5). Add a config version identifier and include it in every generated report. If a mid-quarter change is unavoidable, re-run prior accounts with the new config and note the version change. Alternatively, lock config changes to quarter boundaries. | The worked example captures detailed scoring criteria in Steps 6, 7, and 9 specifically so they can be externalised as config in Stage 5. This constraint ensures that externalisation is meaningful — if the criteria change constantly, config externalisation becomes config management overhead.
Stability / change rate | Zendesk ticket schema (severity levels P1-P4, ticket status values, CSAT rating scale) and Salesforce account object schema (field names for ARR, contract dates, tier, key contacts) remain consistent and do not change during the quarter. | If Zendesk renames severity levels or adds new ones (e.g. introducing P0 for critical outages), the SLA calculations in Step 6 would fail or silently produce incorrect results — the new severity level wouldn't match any SLA target in config. If Salesforce field names change (e.g. a custom field is renamed during a CRM cleanup), Step 1 data retrieval would return empty or error results. | Needs investigation | Stage 5 (data retrieval and parsing code would need updates, SLA config would need new severity entries), Stage 3 (if schemas are unstable, add a schema validation step at workflow start) | Add schema validation at the start of each workflow run: verify that expected fields exist and contain expected value types before proceeding. If a field is missing or has unexpected values, halt the affected step and alert the operator rather than silently continuing with bad data. For Zendesk severity changes, the SLA config should map severity names rather than assuming P1-P4 are fixed. | Schema changes in SaaS platforms are announced but not always communicated to all teams. A CRM admin renaming a custom field can silently break data retrieval. Defensive validation is cheaper than debugging incorrect reports.
Processing model | The agent processes one account at a time, sequentially. The workflow runs for a single account from Step 1 through Step 12 before starting the next account. Batch processing (running all accounts in parallel) is a future enhancement, not a v1 requirement. | If accounts are processed in parallel (e.g. to meet a deadline), API rate limits across all data sources would be hit simultaneously — Slack's 20 requests/minute limit across 50 concurrent account workflows would be exhausted immediately. State management would need to handle concurrent checkpoint writes for different accounts without interference. Error handling for one account's API failure could not be allowed to affect other accounts' processing. | No | Stage 4 (state schema would need account-level isolation, the graph would need a batch orchestration layer above the single-account workflow), Stage 5 (rate limiting would need global coordination across concurrent runs, checkpointing would need account-level namespacing) | For v1, process accounts sequentially. If throughput becomes a bottleneck (e.g. 50+ accounts to review in the first week of the quarter), implement a simple queue: accounts are processed one at a time but the queue manages ordering and tracks completion. True parallelism is a v2 enhancement that requires rate limit pooling and concurrent state management. | Sequential processing is simpler to build, debug, and trust. The quarterly cadence means throughput pressure is concentrated in the first week of the quarter — plan the processing schedule accordingly.
Processing model | Slack search results will contain noise (false positives, off-topic messages, automated bot messages) and the workflow is designed to over-retrieve in Step 4 and filter in Step 5. The signal-to-noise ratio varies significantly by account. | If the reverse is true — Slack results are too sparse or too clean — the sentiment analysis in Step 5 would lack sufficient data points to form a reliable sentiment reading. Accounts with minimal Slack activity would get an 'insufficient data' flag, which is correct behavior, but if many accounts fall into this category, the sentiment dimension becomes uninformative across the portfolio. | No | Stage 3 (if Slack coverage is too sparse, consider adding alternative sentiment sources — e.g. email tone analysis, NPS survey data), Stage 5 (the Slack retrieval node may need to search broader date ranges or additional channels to increase coverage) | For accounts with sparse Slack data: (1) mark sentiment as 'insufficient data' rather than guessing, (2) surface this gap in the report so the CSD can manually supplement, (3) consider expanding search to include email or other communication channels as alternative sentiment sources in v2. | The over-retrieve-then-filter design is intentional. The cost of retrieving too many Slack messages is low (the LLM can process them in Step 5). The cost of missing a critical signal is high (incorrect sentiment assessment leading to wrong health score).